## Charts
HIT SQUAD / PROJECT CONTROLS
Sample Refinery · SAMPLE Boiler Outage PPR · Wood River — Roxana, IL
Cost, Progress & Performance Report
(1) Total Project PPR · Job SAMPLE-2026-017 · 2026 · Wood River — Roxana, IL
Status Date 2026-09-03 · Status: In progress · Prepared by: Hit Squad Project Controls
SAMPLE — synthetic hours and dollars for Look QA. Not a client actual.
Full job cost board — Direct, Indirect, Per diem/travel, Equipment, Rentals, Subs, Materials, hours. PPR field grid follows.
Current Forecast $ | Dollars Expended To Date | Physical % Complete | Hours To Go
65135.6 | 39060 | 45% | 242
Steel = live-pack forecast · Amber = Turnip expended · Every major PPR cost lane has a graph. Dense field grid is on Total Project PPR. |  |  |  | board

## Cover
HIT SQUAD / PROJECT CONTROLS
Sample Refinery · SAMPLE Boiler Outage PPR · Wood River — Roxana, IL
Cost, Progress & Performance Report
(1) Total Project PPR · Job SAMPLE-2026-017 · 2026
Status Date 2026-09-03 · Status: In progress · Prepared by: Hit Squad Project Controls
SAMPLE — synthetic hours and dollars for Look QA. Not a client actual.
Field | Detail | PPR snapshot | Value
Client | Sample Refinery | Current Forecast $ | 65135.6
Job | SAMPLE Boiler Outage PPR | Dollars Expended To Date | 39060
Site | Wood River — Roxana, IL | Workhours Budget | 440
Job # | SAMPLE-2026-017 | Hours Expended To Date | 264
Status Date | 2026-09-03 | Hours Earned To Date | 198
Estimate status | In progress | Physical % Complete | 45%
Prepared by | Hit Squad Project Controls | Performance To Date | 0.75
Notes | SAMPLE status — invented hours and dollars only | Hours To Go | 242
Charts lead the package. Budget from this job’s live estimate pack. Actuals from Turnip T3 Export 15 / 16 through the Status Date. Yellow = Expended. Cyan = Earned.

## Total Project PPR
HIT SQUAD / PROJECT CONTROLS
Sample Refinery · SAMPLE Boiler Outage PPR · Wood River — Roxana, IL
Cost, Progress & Performance Report
(1) Total Project PPR · Job SAMPLE-2026-017 · 2026 · Wood River — Roxana, IL
Status Date 2026-09-03 · Status: In progress · Prepared by: Hit Squad Project Controls · Produced by Hit Squad Project Controls
SAMPLE — synthetic hours and dollars for Look QA. Not a client actual.
| Dollars Budget |  |  | Workhours Budget |  |  | Wage Rate |  | Work Hours Expended |  | Dollars Expended |  | Work Hours Earned |  | Physical % Complete |  | Performance
| $ |  |  | Hrs |  |  | $ / Hr |  | Hrs |  | $ |  | Hrs |  | %
| Original | Revised | Current Forecast | Original | Revised | Current Forecast | Budget Rate | Actual Rate | Daily | To Date | Daily | To Date | Daily | To Date | Daily | To Date | To Go Forecast | To Date | Hours To Go
DIRECT LABOR
Pipefitter Journeyman | 17152.32 | 17152.32 | 17152.32 | 160 | 160 | 160 | 107.202 | 105.6 | 60 | 100 | 5280 | 10560 | 24 | 72 | 15% | 45% | 6592.32 | 0.72 | 88
Boilermaker Journeyman | 14071.2 | 14071.2 | 14071.2 | 120 | 120 | 120 | 117.26 | 116.4706 | 38 | 68 | 3960 | 7920 | 18 | 54 | 15% | 45% | 6151.2 | 0.79412 | 66
Subtotal Direct Labor | 31223.52 | 31223.52 | 31223.52 | 280 | 280 | 280 | 111.5126 | 110 | 98 | 168 | 9240 | 18480 | 42 | 126 | 15% | 45% | 12743.52 | 0.75 | 154
INDIRECT LABOR
Foremen | 4548.96 | 4548.96 | 4548.96 | 40 | 40 | 40 | 113.724 | 130 | 12 | 24 | 1560 | 3120 | 9.6 | 18 | 24% | 45% | 1428.96 | 0.75 | 22
Support | 0 | 0 | 0 | 80 | 80 | 80 | 0 | 80 | 24 | 48 | 1920 | 3840 | 19.2 | 36 | 24% | 45% | -3840 | 0.75 | 44
Staff | 4823.12 | 4823.12 | 4823.12 | 40 | 40 | 40 | 120.578 | 150 | 12 | 24 | 1800 | 3600 | 9.6 | 18 | 24% | 45% | 1223.12 | 0.75 | 22
Per Diem | 2640 | 2640 | 2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910 | 1820 | 0 | 0 | 0% | 0% | 820 | 0 | 0
Mileage / Travel | 280 | 280 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 280 | 0 | 0
Weather Delays | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0
Onboarding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0
Subtotal Labor / PD | 43515.6 | 43515.6 | 43515.6 | 440 | 440 | 440 | 98.8991 | 116.8939 | 146 | 264 | 15430 | 30860 | 80.4 | 198 | 18.27% | 45% | 12655.6 | 0.75 | 242
MATERIALS & SUBCONTRACTS
Materials | 1020 | 1020 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 1020 | 0 | 0
Company Owned Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0
Subcontractors | 18200 | 18200 | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | 8200 | 0 | 0 | 0% | 0% | 10000 | 0 | 0
3rd Party General Rentals | 2400 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2400 | 0 | 0
Subtotal Material & Subcontracts | 21620 | 21620 | 21620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | 8200 | 0 | 0 | 0% | 0% | 13420 | 0 | 0
TOTAL PROJECT | 65135.6 | 65135.6 | 65135.6 | 440 | 440 | 440 | 148.0355 | 147.9545 | 146 | 264 | 19530 | 39060 | 80.4 | 198 | 18.27% | 45% | 26075.6 | 0.75 | 242
Notes | SAMPLE status — invented hours and dollars only · Earned Mhr from 01 DailyReport_TOTAL KPI on Cost report (Summary Phase Grand Total). Physical % = earned / Direct budget hours (hours win if Earned % was also typed). Support earned = Direct % × Support budget hours. Budget from the live Hit Squad estimate pack — not Mike’s Estimate Summary links.
Note on A29: Earned Mhr from 01 DailyReport_TOTAL KPI on Cost report (Summary Phase Grand Total). Physical % = earned / Direct budget hours (hours win if Earned % was also typed). Support earned = Direct % × Support budget hours. Budget from the live Hit Squad estimate pack — not Mike’s Estimate Summary links.

## Hrs S-curve
HIT SQUAD / PROJECT CONTROLS
Sample Refinery · SAMPLE Boiler Outage PPR · Wood River — Roxana, IL
Hours S-curve · steel = live-pack estimate · amber = T3 Export 16 spent
Date | Est hours | Act hours | Cum est hours | Cum act hours | Est headcount | Act headcount
2026-09-01 | 90 | 90 | 90 | 90 | 9 | 9
2026-09-02 | 90 | 90 | 180 | 180 | 9 | 9
2026-09-03 | 90 | 36 | 270 | 216 | 9 | 4
2026-09-04 | 90 | 0 | 360 | 216 | 9 | 0
Cumulative hours — estimate vs actuals
Steel = live-pack estimate · Amber = T3 Export 16 Units · chart-ready columns D / E

## Report log
HIT SQUAD / PROJECT CONTROLS
Sample Refinery · SAMPLE Boiler Outage PPR · Wood River — Roxana, IL
Dated daily report log
Status date | Saved | Forecast $ | Expended $ | Budget hours | Expended hours | Notes
2026-09-03 | 1970-01-01 00:00:00 | 66540.9 | 39060 | 360 | 264 | SAMPLE status — invented hours and dollars only
2026-09-01 | 1970-01-01 00:00:00 | 66540.9 | 19530 | 360 | 132 | SAMPLE day 1 — synthetic Turnip paste

## T3 Export 15
HIT SQUAD / PROJECT CONTROLS
Sample Refinery · SAMPLE Boiler Outage PPR · Wood River — Roxana, IL
T3 Export 15 — Client Cost Analysis · Status Date 2026-09-03
ChargeCode | WO_Description | LaborTotal_ClientActual_Units | LaborTotal_ClientActual_Dollars | PD_ClientActual_Dollars | Other_ClientActual_Units | TotalDollars_ClientActual
100 | Direct Labor | 168 | 18480 | 0 | 0 | 18480
400 | Foremen | 24 | 3120 | 0 | 0 | 3120
500 | Support | 48 | 3840 | 0 | 0 | 3840
505 | Per Diem | 0 | 0 | 1820 | 0 | 1820
702 | Staff | 24 | 3600 | 0 | 0 | 3600
721 | Materials | 0 | 0 | 0 | 12 | 980
725 | 3rd Party General Rentals | 0 | 0 | 0 | 1 | 2100
727 | Company Owned Equipment | 0 | 0 | 0 | 2 | 1600
730 | Subcontractors | 0 | 8200 | 0 | 0 | 8200

## T3 Export 16
HIT SQUAD / PROJECT CONTROLS
Sample Refinery · SAMPLE Boiler Outage PPR · Wood River — Roxana, IL
T3 Export 16 — Client Craft Analysis · Status Date 2026-09-03
event_dt | craft | employee | Units | ST_Units | OT_Units | DT_Units | ChargeCode | Headcount
2026-09-01 | Pipefitter Journeyman | SAMPLE-101 | 40 | 32 | 8 | 0 | 100 | 4
2026-09-01 | Boilermaker Journeyman | SAMPLE-201 | 30 | 24 | 6 | 0 | 100 | 3
2026-09-01 | Firewatch | SAMPLE-301 | 20 | 16 | 4 | 0 | 500 | 2
2026-09-02 | Pipefitter Journeyman | SAMPLE-101 | 40 | 32 | 8 | 0 | 100 | 4
2026-09-02 | Boilermaker Journeyman | SAMPLE-201 | 30 | 24 | 6 | 0 | 100 | 3
2026-09-02 | Firewatch | SAMPLE-301 | 20 | 16 | 4 | 0 | 500 | 2
2026-09-03 | Pipefitter Journeyman | SAMPLE-101 | 20 | 16 | 4 | 0 | 100 | 2
2026-09-03 | Boilermaker Journeyman | SAMPLE-201 | 8 | 8 | 0 | 0 | 100 | 1
2026-09-03 | Firewatch | SAMPLE-301 | 8 | 8 | 0 | 0 | 500 | 1

## _ChartData (hidden)
HIT SQUAD / PROJECT CONTROLS
Chart source — hidden helper
Ranges referenced by the Charts dashboard and Hrs S-curve.
Vendor | Amount | Cost element | Forecast $ | Expended $ | Direct craft | Forecast $ | Expended $ | Indirect | Forecast $ | Expended $ | Per diem / travel | Forecast $ | Expended $ | Equipment / rentals | Forecast $ | Expended $ | Materials / other | Forecast $ | Expended $ | Craft | Hours | Headcount
SAMPLE NDE | 6500 | Direct Labor | 31223.52 | 18480 | Pipefitter Journeyman | 17152.32 | 10560 | Foremen | 4548.96 | 3120 | Per Diem | 2640 | 1820 | Company Owned Equipment | 0 | 0 | Materials | 1020 | 0 | Pipefitter Journeyman | 100 | 4
SAMPLE Insulation | 4200 | Indirect labor | 9372.08 | 10560 | Boilermaker Journeyman | 14071.2 | 7920 | Support | 0 | 3840 | Mileage / Travel | 280 | 0 | 3rd Party Rentals | 2400 | 0 | Weather Delays | 0 | 0 | Boilermaker Journeyman | 68 | 3
SAMPLE Scaffold | 3800 | Per diem / travel | 2920 | 1820 |  |  |  | Staff | 4823.12 | 3600 | [6 empty] | Onboarding | 0 | 0 | Firewatch | 48 | 2
SAMPLE Crane | 3700 | Equipment (COE) | 0 | 0
|  | 3rd Party Rentals | 2400 | 0
|  | Subcontractors | 18200 | 8200
|  | Materials / other | 1020 | 0