## Summary Page
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Rollup line | Amount $ | Man-hours (MH)
Staff labor $
Foremen labor $
Direct labor $
Support labor $
Labor $
Per diem $
Man-hours
Staff travel $
Misc $
Equipment rental $
Tensioning / torquing $
Crane rental $
COE $
Subcontractor $
6.5% markup | 313.5
ESTIMATE TOTAL $

## ORG Chart
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Position | Name | Lane | Shift | Count | Reports to
Lead Safety 01 | Lead Safety 01 | staff | Days | 1 | Company
Superintendent 01 | Superintendent 01 | staff | Days | 1 | Company
Pipefitter GF Union | Pipefitter GF Union | generalForeman | Days | 1 | Lead Safety 01
Boilermaker Foreman | 1 | foreman | Days | 1 | Pipefitter GF Union

## Slicer Hrs
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Phase | ST Hrs | OT Hrs | DT Hrs | Hours
Mechanical Window | 580 | 260 | 140
TOTAL

## Staff
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Shift | Total Billable | Position | Sub Total $ | Rate | Type | ST Hrs | OT Hrs | DT Hrs | PD Days | Labor $ | 2026-09-01
DAYSHIFT |  | Lead Safety 01 |  |  | TITLE | [12 empty] | st-1¦day
[5 empty] | HC | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | st-1¦day
Enter Hours Per shift Here |  |  |  |  | HPS | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | st-1¦day
[5 empty] | ST | [12 empty] | st-1¦day
[5 empty] | OT | [12 empty] | st-1¦day
[5 empty] | DT | [12 empty] | st-1¦day
|  |  |  | 140 | PD | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | st-1¦day
DAYSHIFT |  | Superintendent 01 |  |  | TITLE | [12 empty] | st-2¦day
[5 empty] | HC | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | st-2¦day
Enter Hours Per shift Here |  |  |  |  | HPS | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | st-2¦day
[5 empty] | ST | [12 empty] | st-2¦day
[5 empty] | OT | [12 empty] | st-2¦day
[5 empty] | DT | [12 empty] | st-2¦day
|  |  |  | 140 | PD | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | st-2¦day
DAYSHIFT |  | Pipefitter GF Union |  |  | TITLE | [12 empty] | gf-1¦day
[5 empty] | HC | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | gf-1¦day
Enter Hours Per shift Here |  |  |  |  | HPS | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | gf-1¦day
[5 empty] | ST | [12 empty] | gf-1¦day
[5 empty] | OT | [12 empty] | gf-1¦day
[5 empty] | DT | [12 empty] | gf-1¦day
|  |  |  | 140 | PD | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | gf-1¦day
TOTAL

## Foremen
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Shift | Total Billable | Position | Sub Total $ | Rate | Type | ST Hrs | OT Hrs | DT Hrs | PD Days | Labor $ | 2026-09-01
DAYSHIFT |  | Boilermaker Foreman |  |  | TITLE | [12 empty] | fm-1¦day
[5 empty] | HC | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | fm-1¦day
Enter Hours Per shift Here |  |  |  |  | HPS | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | fm-1¦day
[5 empty] | ST | [12 empty] | fm-1¦day
[5 empty] | OT | [12 empty] | fm-1¦day
[5 empty] | DT | [12 empty] | fm-1¦day
|  |  |  | 130 | PD | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | fm-1¦day
TOTAL

## Direct
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Shift | Total Billable | Position | Sub Total $ | Rate | Type | ST Hrs | OT Hrs | DT Hrs | PD Days | Labor $ | 2026-09-01
DAYSHIFT |  | Boilermaker Journeyman |  |  | TITLE | [12 empty] | dr-1¦day
[5 empty] | HC | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | dr-1¦day
Enter Hours Per shift Here |  |  |  |  | HPS | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | dr-1¦day
[5 empty] | ST | [12 empty] | dr-1¦day
[5 empty] | OT | [12 empty] | dr-1¦day
[5 empty] | DT | [12 empty] | dr-1¦day
|  |  |  | 130 | PD | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | dr-1¦day
NIGHTSHIFT |  | Boilermaker Journeyman |  |  | TITLE | [12 empty] | dr-1¦night
[5 empty] | HC | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | dr-1¦night
Enter Hours Per shift Here |  |  |  |  | HPS | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | dr-1¦night
[5 empty] | ST | [12 empty] | dr-1¦night
[5 empty] | OT | [12 empty] | dr-1¦night
[5 empty] | DT | [12 empty] | dr-1¦night
|  |  |  | 130 | PD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | dr-1¦night
DAYSHIFT |  | Pipefitter Journeyman |  |  | TITLE | [12 empty] | dr-2¦day
[5 empty] | HC | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | dr-2¦day
Enter Hours Per shift Here |  |  |  |  | HPS | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | dr-2¦day
[5 empty] | ST | [12 empty] | dr-2¦day
[5 empty] | OT | [12 empty] | dr-2¦day
[5 empty] | DT | [12 empty] | dr-2¦day
|  |  |  | 130 | PD | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | dr-2¦day
TOTAL

## Support
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Shift | Total Billable | Position | Sub Total $ | Rate | Type | ST Hrs | OT Hrs | DT Hrs | PD Days | Labor $ | 2026-09-01
DAYSHIFT |  | Fire Watch |  |  | TITLE | [12 empty] | su-1¦day
[5 empty] | HC | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | su-1¦day
Enter Hours Per shift Here |  |  |  |  | HPS | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | su-1¦day
[5 empty] | ST | [12 empty] | su-1¦day
[5 empty] | OT | [12 empty] | su-1¦day
[5 empty] | DT | [12 empty] | su-1¦day
|  |  |  | 130 | PD | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | su-1¦day
TOTAL

## Equipment Rental
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Item | Period | Qty | Periods | Rate $ | Freight $ | Cost $ | Total $
450amp diesel welder | daily | 1 | 7 | 134 | 0
TOTAL

## Tensioning Torquing equipment
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Item | Period | Qty | Periods | Rate $ | Freight $ | Cost $ | Total $
Hydraulic tensioner | daily | 1 | 7 | 80 | 0
TOTAL

## Crane Rental
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Item | Period | Qty | Periods | Rate $ | Freight $ | Cost $ | Total $
Carry deck crane | daily | 1 | 7 | 400 | 0
TOTAL

## OM Crane Subcontractor
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Vendor | Scope | Qty | Rate $ | Affiliate | Cost $ | Markup $ | Total $
O&M Crane | crane lift | 1 | 500 | No
ESTIMATE TOTAL $

## COE
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Item | Period | Qty | Periods | Rate $ | Freight $ | Total $
AIR MOVER | daily | 1 | 7 | 32 | 0
TOTAL

## Staff Travel Cost
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Kind | Travelers | Miles | $ / mile | Total $
Staff | 3 | 40 | 0.7
TOTAL

## Misc Costs
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Item | Description | Qty | Each $ | Total $
Alloy rod | Stainless | 1 | 25
TOTAL

## Rate Tables
HIT SQUAD / PROJECT CONTROLS
Produced by Hit Squad Project Controls · Confidential estimate package
Madison CAT 2 (Pit Stop)
Phillips 66 · Wood River — Roxana, IL · East Coast (PCA0001103)
Produced Sep 4, 2026 | 2026-09-04 17:07
Craft | COMP BW $ | ST Bill $ | OT Bill $ | DT Bill $ | PD Rate
Lead Safety 01 | 52.5 | 91.02 | 122.2 | 153.39 | 140
Superintendent 01 | 76.5 | 121.78 | 167.22 | 212.67 | 140
Pipefitter GF Union | 58.84 | 111.22 | 156.31 | 201.4 | 140
Boilermaker Foreman | 49.1 | 112.62 | 159.07 | 205.52 | 130
Boilermaker Journeyman | 45.6 | 108.38 | 152.78 | 197.19 | 130
Pipefitter Journeyman | 49.03 | 99.33 | 138.69 | 178.05 | 130